## Title
Key | Value
Name of Work ;- | Test Infrastructure Project - generated_test_file_14.xlsx
Agreement No. | AG-3889
Reference to work order or Agreement : | WO-108/2020
Name of Contractor or supplier : | ABC Construction Ltd
Bill Number | BILL-9550
Running or Final | Running
TENDER PREMIUM % | 5
WORK ORDER AMOUNT RS. | 1011284
Date of written order to commence work : | 04-11-2023
St. date of Start : | 15-05-2024
St. date of completion : | 12-03-2025
Date of actual completion of work : | 12-12-2025
Date of measurement : | 03-03-2024

## Work Order
Item No. | Description | Unit | Rate | Quantity Since
01 | Security door installation | Kg | 1587.26 | 84.76
02 | Solar panel installation | SqM | 808.71 | 12.25
03 | CCTV camera installation | Kg | 2581.48 | 69.43
04 | Tree planting and maintenance | Kg | 2532.93 | 58.9
05 | Fire alarm system installation | Nos | 3385.86 | 41.52
06 | Network cabling | Mtr | 4067.86 | 78.55
07 | Roofing with asbestos sheets | SqFt | 2603.8 | 9.11
08 | Installation of LED lights | Rmt | 856.19 | 13.21
09 | Concrete mixing and pouring | Rmt | 3890.05 | 10.17
10 | Window frame installation | CuM | 1807.94 | 33.79
11 | Roofing with asbestos sheets | SqFt | 2210.9 | 60.46
12 | Security door installation | Rmt | 4587.72 | 4.61
13 | Waterproofing treatment with bitumen | Ltr | 3339.06 | 5.21
14 | Sand filling and leveling | Ltr | 4059.47 | 99.77
15 | Plastering in cement mortar 1:6 | Rmt | 473.46 | 24.56
16 | Flooring with vitrified tiles | Ltr | 3317.39 | 29.15
17 | Network cabling | SqFt | 2280.65 | 20.6
18 | Excavation in ordinary soil including dressing of sides and bottom | Nos | 4577.14 | 33.89
19 | Electrical wiring with copper cables | SqM | 1163.89 | 4.2
20 | Plastering in cement mortar 1:6 | CuM | 1457.26 | 80.43
21 | Network cabling | Kg | 3609.52 | 29.62
22 | Steel reinforcement bars installation | No | 3254.57 | 96.31
23 | Roofing with asbestos sheets | SqM | 2678.17 | 1.57
24 | Steel reinforcement bars installation | Ltr | 4009.78 | 48.46
25 | CCTV camera installation | SqFt | 4192.38 | 84.87
26 | Flooring with vitrified tiles | Nos | 575.15 | 88.57
27 | Window frame installation | Mtr | 4989.96 | 24.5
28 | Waterproofing treatment with bitumen | Kg | 1050.21 | 72.74
29 | Security door installation | CuM | 908.29 | 1.42
30 | CCTV camera installation | Ltr | 4126.89 | 37.01
31 | Painting with emulsion paint | Ltr | 550.9 | 41.37
32 | Fire alarm system installation | Kg | 2984.04 | 60.38
33 | Tree planting and maintenance | Kg | 3764.28 | 99.73
34 | Asphalt road construction | Ltr | 3125.64 | 99.51
35 | Sand filling and leveling | No | 1073.23 | 59.65
36 | Excavation in ordinary soil including dressing of sides and bottom | Ltr | 4172.48 | 18.55
37 | Gravel base preparation | CuM | 609.29 | 25.69

## Bill Quantity
Item No. | Description | Unit | Quantity | Rate | Amount